	[image: image1.wmf]GMPTLOGO.DRW


	MASSENA PLANT

P.O. Box 460

Massena, New York

13662-0460


	



June 10, 2007
Chief, New York/Caribbean Superfund Branch

Emergency and Remedial Response Division

U.S. Environmental Protection Agency - Region II

290 Broadway, 19th Floor

New York, New York 10007-1866

Attention: GM/Massena Superfund Site Project Manager

Re:
General Motors-Massena Superfund Site, Massena, New York
EPA Orders Index No. II CERCLA-20207 and 20215
-- Monthly Progress Report No. 181 for May 2007
Dear Ms. Anne Kelly:

Enclosed please find one copy of the Monthly Progress Report relating to the activities performed during the month of May 2007, in conformance with the Unilateral Administrative Orders for both operable units of the General Motors Massena Superfund Site.

Should you or your staff have any questions regarding the contents of the Progress Report, please contact me at (315) 764-2233 or Jim Hartnett at (315) 463-2391.

Sincerely,

Douglas C. Premo

GM Project Coordinator

Enclosure: Analytical Tables

I.
Compliance Activities Completed for the Period (May 1 through May 31, 2007)

Raquette River

On May 1, 2007, Outfall 002 (Raquette River) was sampled in accordance with GM’s New York State SPDES permit.  The analytical results are provided in Table 1.
Groundwater Controls
GM began the second round of groundwater sampling at the site on April 30, 2007.  Groundwater sampling was conducted using low flow sampling techniques to obtain representative samples of existing groundwater conditions.  Access continued to be denied to eight monitoring wells located on private property on the St. Regis Mohawk Property.  By May 30, 2007, all 69 remaining groundwater monitoring wells had been sampled.  Water level elevations were also collected from all 69 groundwater monitoring wells.  All groundwater samples were sent to a NY State ELAP certified laboratory for analysis of PCBs, total phenols, 1,2-DCE, TCE, and vinyl chloride.  After the analyses of the groundwater samples have been completed, the analytical results will be validated.  
On May 23, 2007, while collecting groundwater samples from MW-16A and MW-16B, GM collected quarterly groundwater samples from the sump northeast of the Industrial Landfill for analysis of PCBs, total phenols, 1,2-DCE, TCE, and vinyl chloride.  Analytical results are pending. 

On September 25, 2006, GM submitted the draft Quality Assurance Project Plan (QAPP) to USEPA for approval.  GM is awaiting approval from USEPA of this plan.
Mohawk Uplands Soils
On December 4, 2006, GM submitted the draft Mohawk Uplands Remedial Action Work Plan to USEPA for approval.  On January 12, 2007, USEPA provided GM with comments on the Work Plan.  On February 8, 2007, GM provided responses to USEPA’s comments.  On March 26, 2007, USEPA provided comments to GM’s February 8, 2007 responses.  On April 27, 2007, GM provided responses to USEPA’s March 26, 2007 comments.  GM is awaiting approval from USEPA of this plan.
Access to the one property of concern on the St. Regis Mohawk Tribal Reservation (the north parcel) continues to be restricted by the property owner.  The SRMT Environmental Division continues attempting to resolve the access issue with the remaining property owner.
Cove Project
On April 24, 2006, GM submitted the revised draft Cove Remedial Action Completion Report to USEPA for approval.  GM is still awaiting USEPA’s approval of this report.

Maintenance Activities

On January 26, 2007, the draft General Motors Site Inspection, Monitoring and Maintenance Plan (IMMP) was submitted to USEPA for approval.   

During the month of May, a total of approximately 62,160 gallons of water (approximately 46,720 gallons from the sump northeast of the Industrial Landfill and 15,440 gallons from the containment cell areas) were transferred to GM’s WWTS for treatment. 
II.
Analytical Data

Analytical results received during the month of May for the GM Massena Superfund Site include the following:

· Table 1 – Summary of Outfall 002 Water Sampling Analytical Results.

· Table 2 – Summary of Outfall 004 Water Sampling Analytical Results

Results are presented in Attachment 1 of this report. 

III.
Project Tasks Scheduled for the Coming Month (June 2007)

GM anticipates receiving approval from USEPA on the Quality Assurance Project Plan, the GM Site Inspection, Monitoring, and Maintenance Plan, and the Mohawk Uplands Remedial Action Work Plan.  
GM continues to anticipate approval from USEPA on the Cove Remedial Action Completion Report.
IV.
Project Status, Delays and Recovery Plans

In order to provide better visibility of submittals under review, the following table summarizes submittals made during the month, submittals responded to during the month, and submittals, which continue to be under review.
Submitted to EPA / NYSDEC / NYSDOT 
         Date    


- none -
Previously Submitted to EPA - Pending Comment or Approval

Industrial Landfill Final Design Report, Vols. I & II

Apr
27, 2001
Draft Cove Remedial Action Completion Report
Apr
24, 2006

Draft Quality Assurance Project Plan
Sept
25, 2006

Draft GM Site Inspection, Monitoring, and Maintenance Plan
Jan 
26, 2007

St Lawrence River 2006 Monitoring and Maintenance Annual


Inspection Report



Feb 
5, 2007

Draft Mohawk Uplands Remedial Action Work Plan

Apr  27, 2007
Comments/Approvals Received from EPA/DEC/DOT during the Month
- none -
_____________________________________________________________________________

1 copy (excluding plans or reports):

Chief, New York/Caribbean Superfund Branch

Office of Regional Counsel

U.S. Environmental Protection Agency, Region II

290 Broadway, 20th Floor

New York, New York 10007-1866

Attention: GM/Massena Superfund Site Attorney

_____________________________________________________________________________

2 copies (or 5 copies if plan or report):

Emergency and Remedial Response Division

U.S. Environmental Protection Agency, Region II

290 Broadway, 19th Floor

New York, New York 10007-1866

Attention: Anne Kelly

_____________________________________________________________________________

2 copies (or 3 if plan or report):

Mr. Ken Jock




For Federal Express Packages:

Environmental Director



SRMT Environmental Division
St. Regis Mohawk Tribe



449 Frogtown Road
412 State Route 37



Akwesasne, NY 13655
Akwesasne, NY 13655





_____________________________________________________________________________

3 copies (or 3 copies if plan or report):

New York State Department of Environmental Conservation

317 Washington Street

Watertown, New York 13601-3787

Attention: Regional Hazardous Waste Engineer – Peter Taylor, P.E.

Peter S. Ouderkirk, P.E. (1 copy)

Lincoln Fancher, Project Geologist (1 copy)

_____________________________________________________________________________

1 copy:

Beth K. Guidetti
New York State Department of Health

Flanigan Square, Room 300
547 River Street

Troy, New York 12180

_____________________________________________________________________________

1 copy:

Michael Cox- Project Inspector 

NYSDEC – Potsdam Sub Office

6739 US Highway 11

Potsdam, New York  13676

All Reports and Gov't Correspondence:

William J. McFarland



General Motors Corporation







Worldwide Facilities Group







Environmental and Regulatory Support







Remediation Team







Pontiac Centerpoint Campus - Central  







MC 483-520-190







2000 Centerpoint Parkway







Pontiac, Michigan 48341-3147

Phone: 248-753-5816

Thomas L. Arnett, Esq.



General Motors Corporation







Legal Staff

Mail Code 482-C24-D24

300 Renaissance Center

P.O. Box 300

Detroit, MI 48265-3000

Phone: (313) 665-4870 GM: 8-255-4870

Fax: (313) 665-4896  GM: 8-255-4896

Doris Powers Toney



GM Powertrain Global Headquarters






Communications Staff

Mail Code 483-720-560

777 Josyln Avenue

Pontiac, MI 48340-2920

Phone:  (248) 857-1160 GM: 8-237-1160
Fax:  (248) 857-0045  GM: 8-237-0045

Douglas C. Premo
General Motors Powertrain Group - Massena Plant

Rt. 37 East, Box 460

Massena, NY 13662-0460

Phone: 315-764-2233  GM 8-344-2233

Fax: 315-764-2297  GM 8-344-2297

James F. Hartnett




General Motors Corporation




1 General Motors Drive STE2







Syracuse, NY 13206-1127

Phone: 315-463-2391

Fax: 315-432-5197

Joseph A. Detor




ARCADIS/BBL Environmental Services, Inc.




6723 Towpath Road, PO Box 66







Syracuse, NY 13214-0066

Phone: 315-671-9419

ATTACHMENT 1

Analytical Data

May 2007 Monthly Progress Report Massena 


[image: image1.wmf]