	[image: image1.wmf]GMPTLOGO.DRW


	MASSENA PLANT

P.O. Box 460

Massena, New York

13662-0460


	



July 10, 2006
Chief, New York/Caribbean Superfund Branch

Emergency and Remedial Response Division

U.S. Environmental Protection Agency - Region II

290 Broadway, 20th Floor

New York, New York 10007-1866

Attention: GM/Massena Superfund Site Project Manager

Re:
General Motors-Massena Superfund Site, Massena, New York
EPA Orders Index No. II CERCLA-20207 and 20215
-- Monthly Progress Report No. 170 for June 2006
Dear Ms. Anne Kelly:

Enclosed please find one copy of the Monthly Progress Report relating to the activities performed during the month of June 2006, in conformance with the Unilateral Administrative Orders for both operable units of the General Motors Massena Superfund Site.

Should you or your staff have any questions regarding the contents of the Progress Report, please contact me at (315) 764-2233 or Jim Hartnett at (315) 463-2391.

Sincerely,

Douglas C. Premo

GM Project Coordinator

Enclosure: Analytical Tables

I.
Compliance Activities Completed for the Period (June 1 through June 30, 2006)

Raquette River

GM is awaiting comments from the NYDEC in regards to the proposed corrective measures to Outfall 002.
On June 14, 2006, Outfalls 002 (Raquette River) and 004 (north of the Industrial Landfill) were sampled in accordance with GM’s New York State SPDES permit.  Both outfalls were resampled on June 22, 2006 to confirm the analytical results.  These analytical results are presented in Table 1 & 2, Attachment 1.
Groundwater Design
A total of approximately 50,630 gallons of water from the sump northeast of the Industrial Landfill was transferred to GM’s WWTS for treatment during the month of June.
Based on the May 23, 2006, meeting with the USEPA, NYSDEC, and the SRMT in Syracuse, New York, GM has begun the process of writing a draft Monitoring Well Installation and Groundwater Sampling Work Plan and new site QAPP.  Both documents will be submitted to USEPA for approval.  On June 6, 2006, CDM visited the GM Massena site to lay-out and stake locations for the new groundwater monitoring wells.
On June 14, 2006, GM collected quarterly groundwater samples from the sump northeast of the Industrial Landfill.  Analytical results are pending. 

Mohawk Uplands Soils
On June 13, 2006, USEPA provided to GM a second round of comments on the May 18, 2006 Draft Mohawk Upland Area Soil/Sediment Sampling Plan.  On June 23, 2006 GM provided responses to USEPA’s comments.  GM will begin scheduling and execution of the sampling plan upon receipt of USEPA approval.  
Cove Project
On April 24, 2006, GM submitted the revised DRAFT Cove Remedial Action Completion Report to USEPA for approval.
On June 14, 2006, GM collected quarterly water samples from the Turtle Creek holding pond associated with the Cove project.  Analytical results are pending. 

On June 19, 2006, Sevenson Environmental began demobilization of miscellaneous equipment, a site trailer, and supplies remaining from the Cove Remediation Project.  Sevenson demobilized offsite on June 30, 2006.  

Approval to access the Cove property on the St. Regis Mohawk Reservation was obtained from the property owner on June 21, 2006 for the purpose of repairing a washed out swale.  The swale is located between the Turtle Creek holding pond and the Cove with the washed out portion of the swale measuring approximately 40-feet in length.  On June 23, 2006, Perras Environmental mobilized to the site, repaired the wash out, and completed the reconstruction work the same day.

By June 27, 2006, all disturbed areas had been reseeded with new grass seed and hay mulch.  Water management within the containment cells continued during June.  Routine inspections and maintenance of the containment cells continued throughout the month of June.  A total of approximately 47,460 gallons of storm water was pumped to GM’s WWTS for treatment during the month of June.  
II.
Analytical Data

Analytical results for the GM Massena Superfund Site for the months of June include the following:

· Table 1 – Summary of Outfall 002 Water Sampling Analytical Results.

· Table 2 – Summary of Outfall 004 Water Sampling Analytical Results.

Results are presented in Attachment 1 of this report. 

III.
Project Tasks Scheduled for the Coming Month (July 2006)

Pending USEPA approval of the Mohawk Upland Area Soil/Sediment Sampling Plan, GM will initiate that work. 
GM will continue development of a new site QAPP and monitoring well installation and groundwater sampling plan based on the May 23, 2006, meeting with USEPA, NYSDEC, and the SRMT. 

IV.
Project Status, Delays and Recovery Plans

In order to provide better visibility of submittals under review, the following table summarizes submittals made during the month, submittals responded to during the month, and submittals, which continue to be under review.

Submitted to EPA and NYSDEC during the month
         Date    


GM response to EPA’s June 13, 2006 comments on the DRAFT Mohawk 

Upland Area Soil/Sediment Sampling Plan
June 23, 2006
Previously Submitted to EPA - Pending Comment or Approval

Groundwater Monitoring and Well Abandonment Completion Report
Apr
18, 2001

Industrial Landfill Final Design Report, Vols. I & II

Apr
27, 2001
St. Lawrence River 2005 Monitoring and Maintenance Annual 


Inspection Report


Jan 20, 2006

DRAFT Cove Remedial Action Completion Report
Apr. 24, 2006
DRAFT Mohawk Upland Area Soil/Sediment Sampling Plan
May 18, 2006
Comments/Approvals Received from EPA/DEC/DOT during the Month

EPA comments on the DRAFT Mohawk Upland Area Soil/Sediment 

Sampling Plan


June 13, 2006
_____________________________________________________________________________

1 copy (excluding plans or reports):

Chief, New York/Caribbean Superfund Branch

Office of Regional Counsel

U.S. Environmental Protection Agency, Region II

290 Broadway, 20th Floor

New York, New York 10007-1866

Attention: GM/Massena Superfund Site Attorney

_____________________________________________________________________________

2 copies (or 5 copies if plan or report):

Emergency and Remedial Response Division

U.S. Environmental Protection Agency, Region II

290 Broadway, 19th Floor

New York, New York 10007-1866

Attention: Anne Kelly

_____________________________________________________________________________

2 copies (or 3 if plan or report):

Mr. Ken Jock




For Federal Express Packages:

Environmental Director



St. Regis Mohawk Tribe

St. Regis Mohawk Tribe



Environmental Division

412 State Route 37



82 Indian Village Road

Akwesasne, NY 13665



Akwesasne, NY 13665

_____________________________________________________________________________

3 copies (or 3 copies if plan or report):

New York State Department of Environmental Conservation

317 Washington Street

Watertown, New York 13601-3787

Attention: Regional Hazardous Waste Engineer - Darrell M. Sweredoski, P.E.

Peter S. Ouderkirk, P.E. (1 copy)

Lincoln Fancher, Project Geologist (1 copy)

_____________________________________________________________________________

1 copy:

Ms. Fay Navratil

New York State Department of Health

Center for Environmental Health, Flanigan Square

547 River Street

Troy, New York 12180

_____________________________________________________________________________

1 copy:

Michael Cox- Project Inspector 

NYSDEC – Potsdam Sub Office

6739 US Highway 11

Potsdam, New York  13676

All Reports and Gov't Correspondence:

William J. McFarland



General Motors Corporation







Worldwide Facilities Group







Environmental and Regulatory Support







Remediation Team







Pontiac Centerpoint Campus - Central  







MC 483-520-190







2000 Centerpoint Parkway







Pontiac, Michigan 48341-3147

Phone: 248-753-5816

Thomas L. Arnett, Esq.



General Motors Corporation







Legal Staff

Mail Code 482-C24-D24

300 Renaissance Center

P.O. Box 300

Detroit, MI 48265-3000

Phone: (313) 665-4870 GM: 8-255-4870

Fax: (313) 665-4896  GM: 8-255-4896

Doris Powers Toney



GM Powertrain Global Headquarters






Communications Staff

Mail Code 483-720-560

777 Josyln Avenue

Pontiac, MI 48340-2920

Phone:  (248) 857-1160 GM: 8-237-1160
Fax:  (248) 857-0045  GM: 8-237-0045

Douglas C. Premo
General Motors Powertrain Group - Massena Plant

Rt. 37 East, Box 460

Massena, NY 13662-0460

Phone: 315-764-2233  GM 8-344-2233

Fax: 315-764-2297  GM 8-344-2297

James F. Hartnett




General Motors Corporation




1 General Motors Drive STE2







Syracuse, NY 13206-1127

Phone: 315-463-2391

Fax: 315-432-5197

Joseph A. Detor




BBL Environmental Services, Inc.




6723 Towpath Road, PO Box 66







Syracuse, NY 13214-0066

Phone: 315-671-9419

ATTACHMENT 1

Analytical Data

June 2006 Monthly Progress Report Massena 


[image: image1.wmf]