	[image: image1.wmf]GMPTLOGO.DRW


	MASSENA PLANT

P.O. Box 460

Massena, New York

13662-0460


	



November 10, 2006
Chief, New York/Caribbean Superfund Branch

Emergency and Remedial Response Division

U.S. Environmental Protection Agency - Region II

290 Broadway, 20th Floor

New York, New York 10007-1866

Attention: GM/Massena Superfund Site Project Manager

Re:
General Motors-Massena Superfund Site, Massena, New York
EPA Orders Index No. II CERCLA-20207 and 20215
-- Monthly Progress Report No. 174 for October 2006
Dear Ms. Anne Kelly:

Enclosed please find one copy of the Monthly Progress Report relating to the activities performed during the month of October 2006, in conformance with the Unilateral Administrative Orders for both operable units of the General Motors Massena Superfund Site.

Should you or your staff have any questions regarding the contents of the Progress Report, please contact me at (315) 764-2233 or Jim Hartnett at (315) 463-2391.

Sincerely,

Douglas C. Premo

GM Project Coordinator

Enclosure: Analytical Tables

I.
Compliance Activities Completed for the Period (October 1 through October 30, 2006)

Raquette River

In January, 2006, GM submitted the Massena plant’s proposed corrective action to mitigate detectable PCBs at the discharge of outfall 002 to NYSDEC, NYSDOT, and USEPA.  In March, 2006, GM received comments from the NYSDOT requesting a hydraulic analysis.  On August 10, 2006, GM received notification from NYSDEC accepting the proposed corrective action (see attached DEC letter).  On August 15, 2006, on behalf of GM, BBL Environmental Services submitted a Hydraulic Analysis (Report) to NYSDOT in response to their comment letter.  GM is in the process of preparing a bid package for completing this work.  
On October 9, 2006, GM provided responses to the NYSDOT comments on the requested design.  Also in October, on behalf of GM, BBLES submitted a scope of work to prospective subcontractors to perform the work.

On November 3, 2006, NYSDOT approved GM’s proposed corrective action modifications to the Route 37 storm sewer drain provided GM provided five final items prior to initiation of the work.  Those items included:

· Four sets of plans that apply to the areas within the NYS right-of-way, signed and stamped;

· Three copies of the Highway Work Application (Perm 33);

· Liability insurance (Perm 17);

· A Surety Performance Bond (Perm 44e), and;
· Signed Inspection Agreements (Perm 36 and Perm 50).

GM is currently finalizing items requested by NYSDOT and anticipates beginning this work in early December.

On October 18, 2006, Outfall 002 (Raquette River) was sampled in accordance with GM’s New York State SPDES permit.  The analytical results are provided in Table 1, Attachment 1.
Groundwater Program
On September 1, 2006, GM submitted the draft Groundwater Characterization Sampling and Analysis Work Plan to USEPA for approval.  On September 28, 2006, GM received initial comments from USEPA on the Work Plan.  After GM prepared responses to EPA’s initial comments, a conference call was conducted on October 2, 2006 between GM, USEPA, NYSDEC, the SRMT Environmental Division, and respective consultants, to discuss the GM’s response to USEPA initial comments.  Following the conference call, GM provided revised responses to USEPA.  On October 3, 2006, USEPA provided a second round of responses to GM’s October 2, 2006 revised comments.  On October 5, 2006 GM resubmitted additional responses to USEPA’s second round of responses of October 3, 2006.  
On October 11, 2006, USEPA conditionally approved the Groundwater Characterization Sampling and Analysis Work Plan (Work Plan) provided that the final USEPA comments are followed. 
On October 16, 2006, Aquifer Drilling mobilized to the site to begin drilling and installation of the new groundwater monitoring wells.  A kick-off meeting for the approved Work Plan was held the same day.  CDM provided engineering oversight of Aquifer Drilling.  USEPA and the SRMT Environmental Division also provided oversight of the work.
On October 19, 2006, it was discovered that Aquifer Drilling had used the wrong grain size for packing around the well screens during completion of the monitoring wells.  Grain size #1 sand was used instead of grain size #0 or #00 sand as specified in the work plan.  By November 1, 2006, three of four groundwater monitoring wells were subsequently re-drilled using the correct grain size.  The fourth well will also be re-drilled.   
The following table provides of summary of new wells installed with total depths, stratigraphic unit that the well was completed in, date completed, and screened intervals through November 1, 2006.
	#
	Well ID
	Total Depth
	Screened Interval
	Strata Well Completed In
	Date Completed

	1
	MW-711
	22'
	10'-20'
	Upper Till
	10/23/06

	2
	MW-710R
	42.5'
	30'-40'
	Lower Till
	10/25/06

	3
	MW-712R
	39'
	27'-37'
	Lower Till
	10/25/06

	4
	MW-703
	49'
	37'-47'
	Lower Till
	10/26/06

	5
	MW-709
	17.5'
	5'-15'
	Upper Till
	10/26/06

	6
	MW-702
	38'
	25'-35'
	Upper Till
	10/31/06

	7
	MW-714
	42'
	30'-40'
	Lower Till
	10/31/06

	8
	MW-713
	28.5'
	16'-26'
	Upper Till
	11/1/06

	9
	MW-701R
	23'
	10'-20'
	Fill
	11/1/06

	10
	MW-706
	35'
	30'-32'
	Upper GL
	11/1/06


A total of 18 new groundwater monitoring wells are specified to be installed with contingencies for additional wells if required.  During the drilling of MW-702, one soil sample was collected for laboratory analysis of PCBs, total phenols, vinyl chloride, 1,2-DCE, and TCE from the 18 to 22 depth interval.  
On October 30, 2006, GM’s consultant BBLES mobilized to the site to begin an assessment of existing monitoring wells followed by a round of groundwater sampling of the existing wells.  A total of 49 groundwater monitoring wells were inspected for the presence of LNAPL/DNAPL, sediment accumulation, and general well integrity.  Access was denied to eight existing monitoring wells located on private property on the St. Regis Mohawk Property.  On November 1, 2006, a total of seven existing groundwater monitoring wells had been sampled.  These samples were sent to a NY State ELAP certified laboratory for analysis of PCBs, total phenols, 1,2-DCE, TCE, and vinyl chloride.  Analytical results for these groundwater samples are pending.    

On September 25, 2006, GM submitted the draft Quality Assurance Project Plan (QAPP) to USEPA for approval.  GM is awaiting approval from USEPA of this plan.
On October 18, 2006, Outfall 004 (north of the Industrial Landfill) was sampled in accordance with GM’s New York State SPDES permit.  The analytical results are presented in attached Table 2.  Analytical results from the September 12, 2006, quarterly groundwater samples collected from the sump northeast of the Industrial Landfill are provided in Table 3 attached.  

Mohawk Uplands Soils
Access to the one remaining property of concern on the St. Regis Mohawk Tribal Reservation (the north parcel) continues to be restricted by the property owner.  The SRMT Environmental Division continues attempting to resolve the access issue with the one remaining property owner.
GM has begun preparation of the draft Mohawk Uplands Remedial Action Work Plan for the south parcel property.  Delineation sampling on the south parcel was completed earlier this year.
Cove Project
On April 24, 2006, GM submitted the revised DRAFT Cove Remedial Action Completion Report to USEPA for approval.  GM is still awaiting USEPA’s approval of this report.

Ongoing Maintenance Activities

During the month of October, a total of approximately 33,990 gallons of water from the sump northeast of the Industrial Landfill were transferred to GM’s WWTS for treatment.

A total of approximately 7,840 gallons of storm water was pumped from the containment cells to GM’s WWTS for treatment during the month of October.  

On September 12, 2006, GM collected quarterly water samples from the Turtle Creek holding pond associated with the Cove project.  Analytical results are presented in Table 4, Attachment 1.

II.
Analytical Data

Analytical results for the GM Massena Superfund Site for the months of September include the following:

· Table 1 – Summary of Outfall 002 Water Sampling Analytical Results.

· Table 2 – Summary of Outfall 004 Water Sampling Analytical Results.

· Table 3 - Quarterly Force Main Sump Water Sample NE of the Industrial Landfill.

· Table 4 – Turtle Creek Holding Pond Quarterly Water Sample.
Results are presented in Attachment 1 of this report. 

III.
Project Tasks Scheduled for the Coming Month (November 2006)

GM will continue drilling the new groundwater monitoring wells and continue collecting groundwater samples as specified in the USEPA approved Groundwater Characterization Sampling and Analysis Work Plan.  
GM anticipates being able to submit to USEPA a Remedial Action Work Plan for the Mohawk Uplands Area.  GM continues to anticipate approval from USEPA on the Cove Remedial Action Completion Report.

IV.
Project Status, Delays and Recovery Plans

In order to provide better visibility of submittals under review, the following table summarizes submittals made during the month, submittals responded to during the month, and submittals, which continue to be under review.
Submitted to EPA / NYSDEC / NYSDOT during the month
         Date    


GM response to USEPA’s initial comments on Draft Groundwater WP
Oct 
2, 2006

GM response to EPA’s 10-3-2006 comments on the Groundwater WP
Oct
5, 2006

GM response to NYSDOT on proposed corrective action at outfall 002
Oct
9, 2006
Previously Submitted to EPA - Pending Comment or Approval

Groundwater Monitoring and Well Abandonment Completion Report
Apr 
18, 
2001

Industrial Landfill Final Design Report, Vols. I & II

Apr
27, 2001
St. Lawrence River 2005 Monitoring and Maintenance Annual Report
Jan
20, 2006

Draft Cove Remedial Action Completion Report
Apr
24, 2006

GM response to NYSDOT, Outfall 002 Hydraulic Analysis (Report)
Aug
15, 2006
Draft Groundwater Characterization Sampling and Analysis Work Plan
Sept
1, 2006
Draft Quality Assurance Project Plan
Sept
25, 2006

Comments/Approvals Received from EPA/DEC/DOT during the Month

USEPA initial comments on the Draft Groundwater WP
Sept
28, 2006
USEPA comments to GM’s 10-2-2006 responses on Groundwater WP
Oct
3, 2006
USEPA conditionally approves the Groundwater WP
Oct
11, 2006

NYSDOT approval of GM’s proposed corrective action of outfall 002
Nov 
3, 2006
_____________________________________________________________________________

1 copy (excluding plans or reports):

Chief, New York/Caribbean Superfund Branch

Office of Regional Counsel

U.S. Environmental Protection Agency, Region II

290 Broadway, 20th Floor

New York, New York 10007-1866

Attention: GM/Massena Superfund Site Attorney

_____________________________________________________________________________

2 copies (or 5 copies if plan or report):

Emergency and Remedial Response Division

U.S. Environmental Protection Agency, Region II

290 Broadway, 19th Floor

New York, New York 10007-1866

Attention: Anne Kelly

_____________________________________________________________________________

2 copies (or 3 if plan or report):

Mr. Ken Jock




For Federal Express Packages:

Environmental Director



St. Regis Mohawk Tribe

St. Regis Mohawk Tribe



Environmental Division

412 State Route 37



82 Indian Village Road

Akwesasne, NY 13665



Akwesasne, NY 13665

_____________________________________________________________________________

3 copies (or 3 copies if plan or report):

New York State Department of Environmental Conservation

317 Washington Street

Watertown, New York 13601-3787

Attention: Regional Hazardous Waste Engineer - Darrell M. Sweredoski, P.E.

Peter S. Ouderkirk, P.E. (1 copy)

Lincoln Fancher, Project Geologist (1 copy)

_____________________________________________________________________________

1 copy:

Sharon P. McLelland
New York State Department of Health

Center for Environmental Health, Flanigan Square

547 River Street

Troy, New York 12180

_____________________________________________________________________________

1 copy:

Michael Cox- Project Inspector 

NYSDEC – Potsdam Sub Office

6739 US Highway 11

Potsdam, New York  13676

All Reports and Gov't Correspondence:

William J. McFarland



General Motors Corporation







Worldwide Facilities Group







Environmental and Regulatory Support







Remediation Team







Pontiac Centerpoint Campus - Central  







MC 483-520-190







2000 Centerpoint Parkway







Pontiac, Michigan 48341-3147

Phone: 248-753-5816

Thomas L. Arnett, Esq.



General Motors Corporation







Legal Staff

Mail Code 482-C24-D24

300 Renaissance Center

P.O. Box 300

Detroit, MI 48265-3000

Phone: (313) 665-4870 GM: 8-255-4870

Fax: (313) 665-4896  GM: 8-255-4896

Doris Powers Toney



GM Powertrain Global Headquarters






Communications Staff

Mail Code 483-720-560

777 Josyln Avenue

Pontiac, MI 48340-2920

Phone:  (248) 857-1160 GM: 8-237-1160
Fax:  (248) 857-0045  GM: 8-237-0045

Douglas C. Premo
General Motors Powertrain Group - Massena Plant

Rt. 37 East, Box 460

Massena, NY 13662-0460

Phone: 315-764-2233  GM 8-344-2233

Fax: 315-764-2297  GM 8-344-2297

James F. Hartnett




General Motors Corporation




1 General Motors Drive STE2







Syracuse, NY 13206-1127

Phone: 315-463-2391

Fax: 315-432-5197

Joseph A. Detor




BBL Environmental Services, Inc.




6723 Towpath Road, PO Box 66







Syracuse, NY 13214-0066

Phone: 315-671-9419

ATTACHMENT 1

Analytical Data

October 2006 Monthly Progress Report Massena 


[image: image1.wmf]